## ProjectSchedule
CRM SYSTEM
RED-SPEAR
Team Lead: Salem Wafi |  | Project Start: | 2018-02-15
Team Members: Shankar Shrestha, Ahmed Hussein, Yogendra Adhikari, Suhan Budathoki |  | Display Week: | 1 |  |  | 2018-02-12 | [6 empty] | 2018-02-19 | [6 empty] | 2018-02-26 | [6 empty] | 2018-03-05 | [6 empty] | 2018-03-12 | [6 empty] | 2018-03-19 | [6 empty] | 2018-03-26 | [6 empty] | 2018-04-02 | [6 empty] | 2018-04-09 | [6 empty] | 2018-04-16 | [6 empty] | 2018-04-23 | [6 empty] | 2018-04-30 | [6 empty] | 2018-05-07
 | time axis 2018-02-12 to 2018-05-13
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2018-02-12 to 2018-05-13
Systems Planning - Phase 1
Title Page | Ahmed Hussein | 100% | 2018-02-16 | 2018-02-18 | 3
Table of Contents | Ahmed Hussein | 100% | 2018-02-16 | 2018-04-20 | 64
Letter of introduction from the tem to customer | Suhan Budhathoki | 100% | 2018-02-16 | 2018-03-18 | 31
Team Description | Suhan Budhathoki | 100% | 2018-02-16 | 2018-03-18 | 31
Description of customer/client | Salem Wafi | 100% | 2018-02-14 | 2018-02-18 | 5
System request form | Yogendra Adhikari | 100% | 2018-02-21 | 2018-02-24
Fact finding preparation | All | 100% | 2018-02-21 | 2018-02-26
Results of Fact finding | Yogendra Adhikari | 100% | 2018-02-21 | 2018-02-26
Project Scope and recommendations | Salem Wafi | 100% | 2018-02-16 | 2018-03-04
project Schedule | Shankar Shrestha | 100% | 2018-02-16 | 2018-02-21
Feasibility Analysis | Yogendra Adhikari Suhan Budhathoki | 100% | 2018-03-15 | 2018-03-16
System Design - Phase 2
Legend for Symbols on data flow Diagram | Salem Wafi | 80% | 2018-03-01 | 2018-03-24 | 24
Data Flow Diagrams (DFD) | Salem Wafi | 80% | 2018-03-01 | 2018-03-24 | 24
Decomposition Diagram | Salem Wafi | 0% | 2018-03-01 | 2018-03-24 | 24
Data dictionary | Shankar Shrestha | 0% | 2018-03-01 | 2018-03-24 | 24
Entity Relationship Diagram (ERD) | Yogendra Adhikari | 0% | 2018-03-01 | 2018-03-24 | 24
CRUD Matrix | Suhan Budhathoki | 0% | 2018-03-01 | 2018-03-24
Images of sketches/mock-up for User Interface | Ahmed Hussein | 0% | 2018-03-01 | 2018-03-24
Description of user roles and level of security authorization | Shankar Shrestha | 0% | 2018-03-01 | 2018-03-24
Prototype Implementation - Phase 3
Convert the data model(ERD/Data Stores) to live database table | Suhan Budhathoki | 0% | 2018-03-25 | 2018-04-25 | 32
Create a prototype of a functional System | Shankar Shrestha | 0% | 2018-03-25 | 2018-04-25 | 32
Reports | Yogendra Adhikari | 0% | 2018-03-25 | 2018-04-25 | 32
Queries | Salem Wafi | 0% | 2018-03-25 | 2018-04-25 | 32
Formatting and documentation of the project | Ahmed Hussein | 0% | 2018-03-25 | 2018-04-25 | 32
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.